## Sheet1
Task Name | Start | End | Duration (days)
Requirements - Gather requirements for project | 2017-09-25 | 2017-10-09 | 14
Research - Research into microcontrollers and electronics | 2017-10-09 | 2017-10-28 | 19
Research - Research into Android Development, Machine Learning and MatLab | 2017-10-09 | 2017-10-28 | 19
Chose and evaluate an appropriate tech stack to use | 2017-10-25 | 2017-10-28 | 3
Design - Create UML designs for the framework of the project | 2017-10-30 | 2017-11-12 | 13
Design - Create mock screen layouts for app | 2017-10-30 | 2017-11-05 | 6
Implementation - Buy components, construct and code the sensor | 2017-11-06 | 2017-11-26 | 20
Implementation - Create the foundations of the web server with test coverage in place | 2017-11-13 | 2017-11-19 | 6
Implementation- Select an appropriate machine learning algorithm to use and implement it in MatLab | 2017-11-20 | 2017-12-10 | 20
Report - Construct framework for the final year report | 2017-12-11 | 2017-12-24 | 13
Implementation - Develop Android App | 2018-01-08 | 2018-02-18 | 41
Finialise app and make sure all necessary requirements are met | 2018-02-19 | 2018-03-04 | 13
Start and finish the final year report | 2018-03-05 | 2018-04-15 | 41